## Details_break_down(WBS)
# | Task Module | Features To be implemented | Activities to be done | App Dev (man-day) | Start Date | End Date | Module Total (man-month)
Week 1
1 | Requirement Understanding
|  | 1.1 Project Planning | 1.1.1 Understanding purpose, scope and objectives | 4 | 2023-02-02 | 2023-02-02
|  |  | 1.1.2 Develop project schedule | 2 | 2023-02-02 | 2023-02-02
|  |  | 1.1.3 Develop a delivery plan | 2 | 2023-02-02 | 2023-02-02
|  | 1.2 Requirements Gathering | 1.2.1 Understanding product perspective, functions | 4 | 2023-03-02 | 2023-03-02
|  |  | 1.2.2 Identifying constraints, assumptions and dependencies | 2 | 2023-03-02 | 2023-03-02
|  |  | 1.2.3 Understanding Functional Requirements | 8 | 2023-03-02 | 2023-04-02
|  |  | 1.2.4 Identifying Non-Functional Requirements | 4 | 2023-04-02 | 2023-04-02
|  | 1.3 Prepare Documentation | 1.3.1 Prepare UML Use Case diagram | 2 | 2023-04-02 | 2023-05-02
|  |  | 1.3.2 Prepare UML DFD diagram | 4 | 2023-05-02 | 2023-05-02
|  |  | 1.3.3 Prepare UML ERD diagram | 4 | 2023-05-02 | 2023-06-02
|  |  | 1.3.4 Prepare UML Activity diagram | 2 | 2023-06-02 | 2023-06-02
|  |  | 1.3.5 Prepare UML Class diagram | 4 | 2023-06-02 | 2023-07-02
2 | API Analysis and System Design
|  | 2.1 Analyze API structures and prepare documentation | 2.1.1 Analyze live score API | 2 | 2023-08-02 | 2023-08-02
|  |  | 2.1.2 Analyze recent matches with scoreboard API | 2 | 2023-08-02 | 2023-08-02
|  |  | 2.1.3 Analyze fixtures API | 2 | 2023-08-02 | 2023-08-02
|  |  | 2.1.4 Analyze players profile with search API | 2 | 2023-08-02 | 2023-08-02
|  |  | 2.1.5 Analyze match statistics API | 2 | 2023-09-02 | 2023-09-02
|  |  | 2.2.1 Prepare documentation about API responses | 4 | 2023-09-02 | 2023-09-02
|  | 2.2 Design User Interface (UI) | 2.2.1 Design home page | 8 | 2023-09-02 | 2023-10-02
|  |  | 2.2.2 Design fixture page | 4 | 2023-10-02 | 2023-11-02
|  |  | 2.2.3 Design live and recent match scoreboard | 8 | 2023-11-02 | 2023-12-02
|  |  | 2.2.4 Design match deatils and statistics page | 4 | 2023-12-02 | 13/2/2023
|  |  | 2.2.5 Design players profile page | 4 | 13/2/2023 | 14/2/2023
|  | 2.3 Design database | 2.3.1 Identifying database entities | 8 | 14/2/2023 | 15/2/2023
|  |  | 2.3.2 Analyze relationship between entities | 8 | 15/2/2023 | 16/2/2023
3 | Development
|  | 3.3 Implement live score functionality | 3.3.1 Receive live scores form the API | 2 | 16/2/2023 | 16/2/2023
|  |  | 3.3.2 Show team squad list of the live match | 2 | 16/2/2023 | 16/2/2023
|  |  | 3.3.3 Show match stats like scoreboard, venue, man of the match and match result | 2 | 16/2/2023 | 17/2/2023
|  | 3.4 Implement recent matches with scoreboard functionalities | 3.4.1 Show summary of recent matches | 2 | 17/2/2023 | 17/2/2023
|  | c | 3.4.2 Show match stats like scoreboard, squad list, venue, date, match results, man of the match | 2 | 17/2/2023 | 17/2/2023
|  | 3.5 Implement Fixtures functionalities | 3.5.1 Show whole fixture of the tournament | 2 | 17/2/2023 | 17/2/2023
|  |  | 3.5.2 Show country wise/team-wise players | 2 | 18/2/2023 | 18/2/2023
|  |  | 3.5.3 Show date-wise fixture | 2 | 18/2/2023 | 18/2/2023
|  | 3.6 Implement player search features | 3.6.1 Implement search player by name | 2 | 18/2/2023 | 18/2/2023
|  |  | 3.6.2 Show players data in a box with picture | 2 | 18/2/2023 | 18/2/2023
|  |  | 3.6.3 Show players information, statistics and achievements | 2 | 19/2/2023 | 19/2/2023
c |  | 3.7 Implement wining percentage on live matches | 3.7.1 Develop logic to calculate wining percentage | 2 | 19/2/2023 | 20/2/2023
|  |  | 3.7.2 Implement wining percentage calculation logic | 2 | 20/2/2023 | 20/2/2023
| c | 3.8 Implement get statistics feature | 3.8.1 Show data like Top performer of the tournament, most runs for a batsman, team wise ranking | 4 | 20/2/2023 | 21/2/2023
4 | Quality Assurance and Project closing
| c | 4.1 App testing and quality assurance | 4.1.1 Develop test cases | 8 | 21/2/2023 | 21/2/2023
|  |  | 4.1.2 Conduct system testing | 4 | 22/2/2023 | 22/2/2023
|  |  | 4.1.3 Conduct User Acceptance Testing (UAT) | 8 | 23/2/2023 | 23/2/2023
| c |  | 4.1.4 Fix bugs and defects | 2 | 23/2/2023 | 23/2/2023
|  | 4.2 Project closing | 4.2.1 Revise the project deployment checklist | 4 | 24/2/2023 | 24/2/2023
|  |  | 4.2.2 Deploy the application | 4 | 24/2/2023 | 24/2/2023
2
160